## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MoSCoW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US001 | As a developer, I want to implement the database schema and a seeding script to manage Airlines, Airports, and Flight schedules. | Must Have | Database Setup | Backend Team | Completed
Sprint 1 | Sprint 1 | US002 | As a user, I want a responsive landing page where I can search for flights by Origin, Destination, and Date. | Must Have | US001 | Fullstack | Completed
Sprint 2 | Sprint 2 | US003 | As a user, I want to securely register and login to the platform to start booking flights and view my history. | Must Have | None | Backend Team | Completed
Sprint 2 | Sprint 2 | US004 | As a user, I want to view search results with dynamic prices that update based on demand and seat availability. | Must Have | US002 | Frontend Team | Completed
Sprint 3 | Sprint 3 | US005 | As a system, I want a background engine (Celery/Redis) to simulate demand fluctuations and update ticket prices in real-time. | Should Have | US004 | DevOps | Completed
Sprint 3 | Sprint 3 | US006 | As a system, I want to enforce row-level database locking during seat selection to prevent double-booking issues. | Must Have | US003 | Backend Team | Completed
Sprint 4 | Sprint 4 | US007 | As a user, I want to enter passenger details and review my flight summary before proceeding to payment. | Must Have | US002 | Frontend Team | Completed
Sprint 5 | Sprint 5 | US008 | As a user, I want to simulate a secure payment process and generate a unique PNR for my booking. | Must Have | US007 | Fullstack | Completed
Sprint 6 | Sprint 6 | US009 | As a user, I want to receive an automated email confirmation with a PDF ticket containing a QR code. | Could Have | US008 | Backend Team | Completed
Sprint 6 | Sprint 6 | US010 | As an admin, I want a dashboard to visualize booking statistics and total revenue generated by the system. | Could Have | US008 | Frontend Team | Completed

## Sprint Backlog
US ID | Task ID | Task Description | Start Date | End Date | Team Member | Activity | Status | Est. (Hrs) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13
US001 | T1.1 | Design ER Diagram & Schema for Flights/Seats | 2025-11-18 | 2025-11-19 | Backend 1 | DB Design | Done | 8 | Day 1: 4; Day 2: 4
US001 | T1.2 | Write Python Seeding Script for Flight Data | 2025-11-20 | 2025-11-21 | Backend 2 | Scripting | Done | 6 | Day 3: 3; Day 4: 3
US002 | T2.1 | Build FastAPI Flight Search Endpoint | 2025-11-24 | 2025-11-26 | Backend 1 | API Dev | Done | 10 | Day 5: 4; Day 6: 4; Day 7: 2
US002 | T2.2 | Create Landing Page & Search Form UI | 2025-11-27 | 2025-11-30 | Frontend 1 | UI Dev | Done | 12 | Day 8: 4; Day 9: 4; Day 10: 4
US003 | T3.1 | Implement JWT Auth & User Registration | 2025-12-01 | 2025-12-03 | Backend 2 | Security | Done | 10 | Day 1: 4; Day 2: 4; Day 3: 2
US004 | T4.1 | Develop Pricing Engine Logic (Inventory/Time) | 2025-12-04 | 2025-12-07 | Backend 1 | Algorithm | Done | 12 | Day 4: 4; Day 5: 4; Day 6: 2; Day 7: 2
US005 | T5.1 | Set up Redis/Celery for Async Demand Simulation | 2025-12-08 | 2025-12-11 | DevOps | Infrastructure | Done | 10 | Day 8: 3; Day 9: 3; Day 10: 4
US006 | T6.1 | Implement SELECT FOR UPDATE for Seat Locking | 2025-12-15 | 2025-12-17 | Backend 1 | Transactional | Done | 8 | Day 1: 4; Day 2: 2; Day 3: 2
US007 | T7.1 | Develop Multi-step Booking Form & State | 2025-12-18 | 2025-12-22 | Frontend 1 | UI Dev | Done | 12 | Day 4: 4; Day 5: 4; Day 6: 2; Day 7: 2
US008 | T8.1 | Generate PNR & Atomic Transaction Logic | 2025-12-23 | 2025-12-26 | Backend 2 | Logic | Done | 9 | Day 8: 3; Day 9: 3; Day 10: 3
US009 | T9.1 | Integrate PDF Generator with QR Codes | 2025-12-29 | 2025-12-31 | Backend 1 | PDF Logic | Done | 10 | Day 1: 4; Day 2: 4; Day 3: 2
US009 | T9.2 | Configure SMTP & Email Service | 2026-01-01 | 2026-01-02 | Backend 2 | Integration | Done | 6 | Day 4: 3; Day 5: 3
US010 | T10.1 | Build Admin Dashboard & Revenue Charts | 2026-01-03 | 2026-01-06 | Frontend 1 | Data Viz | Done | 12 | Day 6: 3; Day 7: 3; Day 8: 2; Day 9: 2; Day 10: 2

## Retrospection
SL | Sprint | Start Date | End Date | Team Member Name | Start Doing | Stop Doing | Continue Doing | Action Taken
1 | Sprint 1 | 2025-11-18 | 2025-11-25 | Fullstack Team | Standardizing API response formats | Using static JSON for flight data | Designing clean ER diagrams | Implemented a unified Search API with validation.
2 | Sprint 2 | 2025-11-26 | 2025-12-03 | Backend + Frontend | Using JWT middleware for protected routes | Storing passwords in plain text | Integrating dynamic price UI | Completed Auth system and search-to-pricing integration.
3 | Sprint 3 | 2025-12-04 | 2025-12-11 | Backend + DevOps | Task monitoring via Redis/Celery | Heavy DB calls inside search loops | Optimizing DB locking (Select For Update) | Decoupled demand simulation from the main request cycle.
4 | Sprint 4 | 2025-12-12 | 2025-12-19 | Frontend Team | Building reusable form components | Deeply nested state for passenger info | Ensuring mobile responsiveness | Modularized the multi-step passenger checkout form.
5 | Sprint 5 | 2025-12-20 | 2025-12-27 | Fullstack Team | Atomic transaction logging | Mocking payment without error handling | Generating unique PNR strings | Implemented "all-or-nothing" DB transactions for PNR generation.
6 | Sprint 6 | 2025-12-28 | 2026-01-06 | Fullstack Team | PDF template versioning | Synchronous email triggers | Visualizing revenue metrics | Switched to asynchronous PDF/Email generation for better UX.

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | Day 3 | Flight search performance is slow due to lack of indexing on Origin/Destination columns. | Added B-Tree indexes to airport_code and departure_time in PostgreSQL.
Sprint 2 | Day 2 | JWT tokens expiring too quickly during frontend testing sessions. | Adjusted ACCESS_TOKEN_EXPIRE_MINUTES and implemented a refresh token logic.
Sprint 2 | Day 5 | Pricing engine returning negative values when "Seats Remaining" is high. | Refactored the algorithm to include a Base_Fare floor value.
Sprint 3 | Day 3 | Redis connection failing intermittently on local Docker environment. | Updated CELERY_BROKER_URL and implemented a retry policy for the worker.
Sprint 3 | Day 4 | Race condition: Two users could book the last seat simultaneously during load test. | Implemented with_for_update() row-level locking on the Flight table.
Sprint 4 | Day 2 | Multi-step form state is lost when the user refreshes the page mid-booking. | Implemented localStorage persistence for the passenger detail state.
Sprint 5 | Day 3 | PNR generation producing duplicate strings during high-concurrency simulation. | Switched from a random 6-digit string to a UUID-based hash for uniqueness.
Sprint 5 | Day 5 | Payment simulation hangs because the external mock API is unresponsive. | Wrapped the payment call in a try-except block with a 5-second timeout.
Sprint 6 | Day 2 | PDF generation is timing out the HTTP request because of high image resolution in QR codes. | Moved PDF generation to a Celery background task and used WebSockets for completion alerts.
Sprint 6 | Day 4 | Admin Dashboard charts (Recharts) not rendering properly on mobile screens. | Applied Tailwind CSS responsive wrappers and simplified the SVG chart density.